## summary
# | Category | Count
1 | Bug | 16
2 | Enhancement | 25
3 | Enhancement (Productization) | 16
4 | Clarification | 19
5 | No Change Required | 4
6 | Other / Misc (Purging, Archiving, Landscape, etc.) | 8
GRAND TOTAL |  | 88
# | Priority | Bug | Enhancement | Enh. (Productization) | Clarification | No Change Req. | Other/Misc | TOTAL
1 | High | 11 | 10 | 4 | 0 | 0 | 2 | 27
2 | Medium | 1 | 10 | 1 | 0 | 0 | 1 | 13
3 | Low | 2 | 5 | 10 | 0 | 0 | 0 | 17
4 | NA / Blank | 2 | 0 | 1 | 19 | 4 | 5 | 31
| TOTAL | 16 | 25 | 16 | 19 | 4 | 8 | 88
# | Status | Bug | Enhancement | Enh. (Productization) | Clarification | No Change Req. | Other/Misc | TOTAL
1 | To Be Taken Up | 15 | 13 | 1 | 0 | 0 | 3 | 32
2 | WIP | 0 | 4 | 4 | 0 | 1 | 0 | 9
3 | Closed | 0 | 1 | 0 | 16 | 3 | 0 | 20
4 | Need to Study/Analyze | 1 | 7 | 6 | 3 | 0 | 0 | 17
5 | To Be Done | 0 | 0 | 4 | 0 | 0 | 0 | 4
6 | To Be Tested | 0 | 0 | 0 | 0 | 0 | 2 | 2
7 | Repeated | 0 | 0 | 1 | 0 | 0 | 0 | 1
8 | Not Yet Finalized | 0 | 0 | 0 | 0 | 0 | 3 | 3
| TOTAL | 16 | 25 | 16 | 19 | 4 | 8 | 88

## summ (hidden)
| Criteria → |  |  | Bug | Enhancements | Clarification |  | High | Low | Medium
[5 empty] | Enahancement (Productization) |  |  | HIGH | LOW
|  |  |  | 17 | 55 | 31 | 18 | 60 | 46 | 17
| S.No | Menu Item | Sub Menu Item | BUG | ENHANCEMENT | CLARIFICATION | OTHERS | HIGH | LOW | MEDIUM | TOTAL
DB | 1 | Dashboard | SR | 1 | 0 | 0 | 1 | 0 | 2 | 0 | 2
DB | 2 | Dashboard | PTW | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
DB | 3 | Dashboard | UES | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 4
Meter | 4 | Maintenance Shop | Meter Rollovers | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
Meter | 5 | Maintenance Shop | Meter Replacements | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
Meter | 6 | Maintenance Shop | Meter replacement | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
Meter | 7 | Maintenance Shop | Meter rollover | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
WF | 8 | Scheduled jobs | Work orders | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
Admin | 9 | Config Policies | Password | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
| 10 | Config Policies | Notification | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
APM | 11 | Config Policies | PM generation | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
| 12 | Config Assets | Asset types | 0 | 4 | 1 | -1 | 0 | 0 | 4 | 4
| 13 | Config Assets | Material Types | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1
meter | 14 | Config Assets | Meter Types | 0 | 2 | 1 | 0 | 0 | 2 | 1 | 3
| 15 | General |  | 0 | 2 | 0 | 1 | 0 | 2 | 1 | 3
| 16 | Schedule types |  | 1 | 1 | 3 | -2 | 0 | 2 | 1 | 3
| 17 | Sections |  | 0 | 2 | 0 | 1 | 0 | 2 | 1 | 3
MMP | 18 | Configuration Maintenance | MMP | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 2
| 19 | Config Setup | Master Workflows | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2
| 20 | Config Assets | Car Asset Layout | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2
| 21 | Config Assets | Car types | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2
| 22 | Config Assets | Trainset types | 0 | 2 | 0 | 2 | 0 | 4 | 0 | 4
| 23 | Asset/make/Model vs Sch types | Association of Schedules not only based on asset types, but also based on make and model | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 2
| 24 | Job plan Checklist | based on AT make and model - if situation demands | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2
| 25 | Engineering sections (Sub units/Depts) |  | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2
| 26 | Landscape (Identify impacted landscapes) |  | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2
| 27 | Fault codes |  | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2
| 28 | Functional Units |  | 0 | 1 | 0 | -1 | 0 | 0 | 0 | 0
| 29 | PTW screen |  | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2
| 30 | Job Plan |  | 0 | 1 | 3 | -2 | 0 | 2 | 0 | 2
| 31 | Checksheet |  | 1 | 1 | 1 | -1 | 0 | 0 | 2 | 2
| 32 | Master Maintenance plan |  | 0 | 3 | 4 | -1 | 6 | 0 | 0 | 6
| 33 | WORKORDER |  | 0 | 0 | 1 | -1 | 0 | 0 | 0 | 0
| 34 | Asset PM Master |  | 0 | 3 | 0 | 3 | 6 | 0 | 0 | 6
| 35 |  |  | 3 | 18 | 12 | 0 | 18 | 12 | 5 | 35
| 36 | Configuration Maintenance | Job plans | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2
| 37 | General | Labels, Screen/Form headings | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1
| 38 | Checklist |  | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 2
| 39 | Master Preventive Maintenance Plan |  | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 2
| 40 | PTW dashboard |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 41 | Config Assets | Trainset Meter measurements | 0 | 0 | 1 | -1 | 0 | 0 | 0 | 0
| 42 | Config Users | Users | 0 | 0 | 2 | -2 | 0 | 0 | 0 | 0
| 43 | Config Setup | Locations | 0 | 0 | 1 | -1 | 0 | 0 | 0 | 0
| 44 | Maintenance & Shop | Fitness Certificate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRAND TOTAL |  | 17 | 55 | 31 | 18 | 60 | 46 | 17 | 123

## Observations
S.No | Recorded Date | Source of person/review/test | Category Bug/Productization/New/Edit/Bug | Priority | Complexity | Menu Item | Sub Menu Item | Status | Issue Noted | Developer Remarks | Remarks | Status
1 | 2026-01-06 | Test | Bug | Low | VL | Dashboard | SR | To be taken up | 1) System down color is in green color 2) Color changes required | UI Changes Need to change for red/suitable -(Is system allows to change color legends?) |  | To be taken up
2 | 2026-01-06 | Test | Bug | High | VL | Dashboard | PTW | To be taken up | Permit by - Purpose - Pie chart | Lable to be corrected. Values are not coming | Can be modified with lable names to be corrected to showing results and to populated correctly | To be taken up
3 | 2026-01-06 | Test | Bug | High | VL | Dashboard | UES | To be taken up | Partciapation | To be corrected (spell correction) | Independent spelling correction required - Independent | To be taken up
4 | 2026-01-06 | Test | Enahancement (Productization) | Low | High | Dashboard | UES | To be taken up | Make Lov | Currently showing all makes in the dropdown. Only related makes for the asset should be poplulated. Nice to have - Required more more discussion | Filter missed, Showing all makes | To be taken up
5 | 2026-01-06 | Test | Bug | High | Low | Maintenance Shop | Meter Rollovers | To be taken up | 404 | Delete from the menu | Showing 404 Error | To be taken up
6 | 2026-01-06 | Test | Bug | High | Low | Maintenance Shop | Meter Replacements | To be taken up | 404 | Delete from the menu | Showing 404 Error | To be taken up
7 | 2026-01-06 | Test | Bug | High | Low | Maintenance Shop | Meter replacement | To be taken up | 404 error | Delete from the menu | Not required | To be taken up
8 | 2026-01-06 | Test | Bug | High | Low | Maintenance Shop | Meter rollover | To be taken up | 404 error | Delete from the menu | Not required | To be taken up
9 | 2026-01-06 | Test | Bug | High | Low | Scheduled jobs | Work orders | To be taken up | 404 error | Delete from the menu | Not required | To be taken up
10 | 2026-01-06 | Test | Bug | High | Low | Config Policies | Password | To be taken up | 404 error | Delete from the menu | Not required | To be taken up
11 | 2026-01-06 | Test | Bug | High | Low | Config Policies | Notification | To be taken up | 404 error | Delete from the menu | Not required | To be taken up
12 | 2026-01-06 | Test | Bug | High | Low | Config Policies | PM generation | To be taken up | 404 error | Delete from the menu | Not required | To be taken up
13 | 2026-01-06 | Test | Enhancements | Medium | M | Config Assets | Asset types | To be taken up | Custodian Units | Required clarifications - To be debated | Custodian unit lable change to Dept | To be taken up
14 | 2026-01-06 | Test | Enhancements | Medium | High | Config Assets | Material Types | Need to study | Material types | Required clarifications - To be debated - UOM list to be collected with full forms | Clarification given | Need to study
15 | 2026-01-06 | Test | Enhancements | Medium | Low | Config Assets | Meter Types | Need to study | Meter types | Required clarifications - To be debated - Need to be corrected (Label names) Part names… | Clarification required | Need to study
16 | 2026-01-06 | Test | Enhancements | Low | M | Config Assets | Meter Types | To be taken up | 1) Unable to Add New 2) Edit missed |  | Need review on this | To be taken up
17 | 2026-01-27 | Test | Enhancements | Medium | High | General |  | To be taken up | Make autoreduction can be done while searching | Need to verify auto reduction for all screens, Make autoreduction can be done while searching |  | To be taken up
18 | 2026-01-27 | Test | Enhancements | Low | VL | General |  | To be taken up | Notation required (Add, New etc.,) | Need to verify on the screen | Need review | To be taken up
19 | 2026-01-27 | Test | Enhancements | Medium |  | Schedule types |  | To be taken up | CRUD | CRUD |  | To be taken up
20 | 2026-01-27 | Test | Enhancements | Medium |  | Sections |  | To be taken up | CRUD | CRUD |  | To be taken up
21 | 2026-01-06 | Test | Enhancements | High | High | Configuration Maintenance | MMP | Need to study | Usage frequency (No of hours) |  | New Feature Required - Need discussion | Need to study
22 | 2026-01-06 | Test | Enhancements | Low | VH | Config Setup | Master Workflows | Need to study | Master workflows ??? | Nice to have- To be debated | NA | Need to study
23 | 2026-01-06 | Test | Enhancements | Medium | High | Config Assets | Asset types | Need to study | Unable tp add Specifications /Attachments/Notes | Need to discuss and fulfill the funactionality |  | Need to study
24 | 2026-01-06 | Test | Enhancements | Medium | High | Config Assets | Asset types | Need to study | Models | Need to discuss and fulfill the funactionality |  | Need to study
25 | 2026-01-06 | Test | Enahancement (Productization) | Low | High | Config Assets | Car Asset Layout | To be done as a another asset type | Car Assets |  | "No Add" feature in Front End | To be done as a another asset type
26 | 2026-01-06 | Test | Enahancement (Productization) | Low | High | Config Assets | Car types | To be done as a another asset type | Car types |  | "No Add" feature in Front End | To be done as a another asset type
27 | 2026-01-06 | Test | Enahancement (Productization) | Low | High | Config Assets | Trainset types | To be done as a another asset type | Train Sets |  | "No Add" feature in Front End | To be done as a another asset type
28 | 2026-01-06 | Test | Enahancement (Productization) | Low | High | Config Assets | Trainset types | To be done as a another asset type | Trainset types |  | No Add feature in Front End | To be done as a another asset type
29 | 2026-01-27 | Test | Enahancement (Productization) | High | High | Asset/make/Model vs Sch types | Association of Schedules not only based on asset types, but also based on make and model | To be analyzed the impact and feasibility | If trainset defers what can do | Make, model commbination required | Make, model commbination required | To be analyzed the impact and feasibility
30 | 2026-01-27 | Test | Enahancement (Productization) | Low | High | Job plan Checklist | based on AT make and model - if situation demands | To be analyzed the impact and feasibility |  |  |  | To be analyzed the impact and feasibility
31 | 2026-01-27 | Test | Enahancement (Productization) | Low | High | Engineering sections (Sub units/Depts) |  | To be studied and add ational things prior to implementation | Verify/Explore - How to map/associate related activities of each eng section of a job plan activities | Verify/Explore - How to map/associate related activities of each eng section of a job plan activities |  | To be studied and add ational things prior to implementation
32 | 2026-01-27 | Test | Enahancement (Productization) | Low | High | Landscape (Identify impacted landscapes) |  | To be studied further | Landscape defeinition based on make and model of trainset | Landscape defeinition based on make and model of trainset |  | To be studied further
33 | 2026-01-27 | Test | Enahancement (Productization) | Low | High | Fault codes |  | To be studied | Unable to add System - sub system |  |  | To be studied
34 | 2026-02-09 | Test | Enahancement (Productization) | NA |  | Functional Units |  | To be analyzed | Hirechay view should be changed.(LTMRHLHO & LTMRHLCO)why divided into two parts |  | Need more discussion | To be analyzed
35 | 2026-02-09 | Test | Bug | High | VL | PTW screen |  | To be taken up | Fire premit spelling should be changed to fire permit | To be corrected (spell correction) | Need to review | To be taken up
36 | 2026-02-09 | Test | Bug | Low | VL | Schedule types |  | To be taken up | In landing screen sorting is not working. |  | Need to review and fix it | To be taken up
37 | 2026-02-09 | Test | Enhancements | Low |  | Job Plan |  | To be taken up | In actions(edit) --what is add time --Change the name add time to add item or just add | Change button caption from "Add time" to "Add" | Need to review and fix it | To be taken up
38 | 2026-02-09 | Test | Bug | Medium | VL | Checksheet |  | To be taken up | Checklist -- In landing screen showing name as checklist but in submenu showing as checksheet |  | Need clarifications | To be taken up
39 | 2026-02-09 | Test | Clarification | NA |  | Checksheet |  | To be studied | Sub department (permissions)-who and what should be updated |  | Need clarifications | To be studied
40 | 2026-02-09 | Test | Clarification | NA |  | Master Maintenance plan |  |  | Safety plans are associated with which screen and how |  | Clarification and understanding required
41 | 2026-02-09 | Test | Clarification | NA |  | WORKORDER |  | To be studied | Before approval-execution, material, checksheets, meters tabs are not required after approval only this tabs can be done. | Editing of those tabs are only during the work order execution only | Need clarifications | To be studied
42 | 2026-02-27 | Test | Enhancements | High | High | Asset PM Master |  | To be taken up | Cycle modification required -Dynamic (With Sliding of next schedule ) |  | With Sliding of next schedule ) - Planning & Schedule | To be taken up
43 | 2026-02-27 | Test | Enhancements | High | High | Asset PM Master |  | To be taken up | Add Working hours provision required |  |  | To be taken up
44 | 2026-02-27 | Test | Enhancements | High | High | Asset PM Master |  | To be taken up | Delete option required for as required for correction | Logical deletion | Logical deletion | To be taken up
45 |  | Satyanand | Bug |  |  |  |  | Need to study | Delettion of assets from Asset register | Client Requirements - need to be discussed |  | Need to study
46 |  | Satyanand | Enhancements | HIGH | HIGH |  |  | To be taken up | RST hierarchy | Client Requirements - need to be discussed |  | To be taken up
47 |  | Satyanand | Enhancements | HIGH | HIGH |  |  | To be taken up | Other depts hierarchy | Client Requirements - need to be discussed |  | To be taken up
48 |  | Satyanand | Bug |  |  |  |  | To be taken up after the collection of probable vendor names | Vendor - Unable to add vendor name , if we reduce the name to Grund it is accepting . kindly resolve the Asap | Client Requirements - need to be discussed |  | To be taken up after the collection of probable vendor names
49 |  | Satyanand | Enhancements | HIGH | HIGH |  |  | To be discussed and taken up | dispose/Condemn | Client Requirements - need to be discussed |  | To be discussed and taken up
50 |  | Satyanand | Enhancements | LOW | HIGH |  |  | To be studied | RAP module | Client Requirements - need to be discussed |  | To be studied
51 | 2026-01-06 | Test | Enahancement (Productization) | Low | M | Configuration Maintenance | Job plans | WIP | Sch types - Checklist | New requirement | Clarification required | WIP
52 | 2026-01-27 | Test | Enahancement (Productization) | Medium | Low | General | Labels, Screen/Form headings | WIP | Can make user definable change(Multi lingual) |  |  | WIP
53 | 2026-01-27 | Test | Enhancements | High |  | Checklist |  | WIP | Add new check list | Add new check list |  | WIP
54 | 2026-01-27 | Test | Enhancements | High | High | Master Preventive Maintenance Plan |  | WIP | Need to show shcedule maintenance cycle plan for assets |  | Need review | WIP
55 | 2026-02-09 | Test | Enhancements | Medium |  | Checksheet |  | WIP | Mandatory fields to be defined |  | Need to review | WIP
56 | 2026-02-09 | Test | Enahancement (Productization) | High | M | Master Maintenance plan |  | WIP | Asset type list dropdown is right or wrong need clarification |  | Need clarifications | WIP
57 | 2026-02-09 | Test | No Change Required | NA |  | Master Maintenance plan |  | WIP | For all asset types how to generate pattern | Only for one asset can be generated | Need to review | WIP
58 | 2026-02-09 | Test | Enahancement (Productization) | High | M | Master Maintenance plan |  | WIP | Category list showing all categories (should show depending on asset type) |  | Need to review and fix it | WIP
59 |  | Satyanand | Enhancements | HIGH | HIGH |  |  | WIP | MMS | Client Requirements - need to be discussed |  | WIP
60 | 2026-02-09 | Test | Clarification | NA |  | Master Maintenance plan |  | Closed | Does asset type has schedule cycle or not | Assets and routes has schedule cycles | Need clarifications | Closed
61 | 2026-02-09 | Test | Clarification | NA |  | Master Maintenance plan |  | Closed | Clarifcation for asset type & category LOV -required flags should be shown | Need to review | Need to review | Closed
62 | 2026-02-09 | Test | Clarification | NA |  | Master Maintenance plan |  | Closed | Asset type,category,scheduletype,safety plan, job plan |  | Clarification and understanding required | Closed
63 | 2026-02-09 | Test | Clarification |  |  | Schedule types |  | Closed | what is reliability enhancing program |  | Clarification eceived | Closed
64 | 2026-02-09 | Test | Clarification | NA |  | Job Plan |  | Closed | Landing screen -- schedule list is showing only 37 Types .Why? | Need to verify | Clarification eceived | Closed
65 | 2026-02-09 | Test | Clarification | NA |  | Job Plan |  | Closed | Schedules-By what basis this list is defined | Need to verify | Clarification eceived | Closed
66 | 2026-02-09 | Test | Clarification |  |  | Job Plan |  | Closed | What is MN-- why it is dfined in shortcut in LOV also make the list values in Shortcut | ` | Clarification eceived | Closed
67 | 2026-02-09 | Test | No Change Required | NA |  | PTW dashboard |  | Closed | Permit by purpose to" type of permit " | No Change required | No Change required | Closed
68 | 2026-02-09 | Test | Clarification | NA |  | Schedule types |  | Closed | There are total 77 types but in screens showing only 37 Types .Why? | Relative schedule types are showing | Clarification eceived | Closed
69 | 2026-02-09 | Test | Clarification | NA |  | Schedule types |  | Closed | In service it is showing House keeping , whereas house keeping itself has been defined as one of the type |  | Clarification eceived | Closed
70 | 2026-01-06 | Test | Clarification | NA |  | Config Assets | Trainset Meter measurements | Closed |  |  | Clarification required | Closed
71 | 2026-01-06 | Test | Clarification | NA |  | Config Users | Users | Closed | Primary role |  | Clarification required | Closed
72 | 2026-01-06 | Test | Clarification | NA |  | Config Users | Users | Closed | Secondary role |  | Clarification required | Closed
73 | 2026-01-06 | Test | Clarification | NA |  | Config Assets | Meter Types | Closed | Reading Type | Reading Type - DELTA, Actual | Required clarifications | Closed
74 | 2026-01-06 | Test | Enhancements | Medium |  | Config Assets | Asset types | Closed | Asset Functional category | Required clarifications | Clarification given | Closed
75 | 2026-01-06 | Test | Clarification | NA |  | Config Setup | Locations | Closed | Locations |  | ??? - Required clarifications (parent, parent code, site…etc) | Closed
76 | 2026-01-06 | Test | Clarification | NA |  | Config Assets | Asset types | Closed | Groups |  | ??? - Required clarifications (Assembly, Linear,Group,..etc ) | Closed
77 | 2026-01-06 | Test | No Change Required | NA |  | Dashboard | SR | Closed | Is Re-Open feature availavble | Feaure is not available, and this feature is not required. | Need to verify | Closed
78 | 2026-01-06 | Test | No Change Required | NA |  | Dashboard | SR | Closed | Can SR route with another Dept | User can route SR from one dept. to another dept. | Need to verify | Closed
79 | 2026-01-06 | Test | Clarification | NA |  | Dashboard | UES | Closed | What is Assembly and Component | Clarification received | Clarification received | Closed
80 | 2026-02-09 | Test | Enahancement (Productization) | High | High | Master Maintenance plan |  | Repeated | operational hours --make,model |  | Need to review and fix it | Repeated
81 |  |  | Identification of product setup data | High | Med |  |  | To be taken up | List out tables and lookup values which are used for the funcationality implementation or business logic implementation |  |  | To be taken up
82 |  |  | Purging |  |  |  |  | To be taken up | identify tables to be purged periodically
83 |  |  | Archeiving |  |  |  |  | To be taken up | identify tables to be archieved periodically
84 |  |  | Landscape - New asset position creation | High | H |  |  | TO be Tested |  |  |  | TO be Tested
85 |  |  | Landscape - New asset type addition | Medium | H |  |  | TO be Tested |  |  |  | TO be Tested
86 |  |  | Data loading through excel imports | [8 empty] | Requirements not yet Finalised
87 |  |  | Pm on fixed dates |  |  |  |  | Requirements not yet Finalised |  |  |  | Requirements not yet Finalised
88 |  |  | verify created by and updated by | [5 empty] | ??
102
103
104 | [5 empty] | Maintenance & Shop | Fitness Certificate |  | 404 error
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135

## EditableNon Editable
S.No | Menu | Submenu | Editable | Non Editable | Remarks | Priority | Editable Fields
1 | Configuration Setup | Organisations | No | Yes | There is no edit option to update the details
2 | Configuration Setup | Functional Units | No | Yes | There is no edit option to update the details
3 | Configuration Setup | Designation | No | Yes | There is no edit option to update the details
4 | Configuration Setup | Workflow Master |  |  | Unable to show details while clicking search filter it is showing error message --- Http failure response for http://192.168.14.61/services/workflowService/api/workflow/get-workflow-template-list: 500 Internal Server Error
5 | Configuration Asset | Meter Types | No | Yes | There is no edit option to update the details
6 | Configuration Asset | Car Types | No | Yes | There is no edit option to update the details
7 | Configuration Asset | Trainset Types | No | Yes | There is no edit option to update the details
8 | Configuration Users | Staff |  |  | In staff landing screen there are two options to edit and it is navigating to same screens -- 1. edit option , 2. Hyperlink on staff number
9 | Configuration Maintenance | Schedule Types | No | Yes | There is no edit option to update the details
10 | Configuration Maintenance | Checklists | Yes | No | In submenu list name is showing as checklists, when opened it is showing as check sheets
11 | Asset Register | Assets |  |  | In ASSETS landing screen there are two options to edit and it is navigating to same screens -- 1. edit option , 2. Hyperlink on staff number
12 | Asset Register | Asset routes |  |  | What is use of select ?? Edit option can be without selecting also then what is the use of select option.
13 | Maintenance Shop | Meter Measurements | No | Yes | There is no edit option to update the details
14 | Maintenance Shop | Assets under monitoring | No | Yes | There is no edit option to update the details
15 | Service Requests | Service Request |  |  | In SR landing screen there are two options to edit and it is navigating to same screens -- 1. edit option , 2. Hyperlink on staff number